## Extracted Tables
Table 1 -- P1_Table_1
SUMMARY OF BUILDING. | COSTS.COST PLAN NR 1 |  | Groundworks £ | Main Works £ | TOTAL £ | Total Gross Internal.m² 8,341.£/m² | Total Gross Internal.sq. ft. 89,783.£/sqft | NRM Code | NRM Description | Match Confidence
1 | Demolition and Alteration |  | 25,000 | 90,000 | 115,000 | 13.79 | 1.28 | 7.1.1 | Minor demolition and alteration works | 0.93
2 | Enabling Works |  | 920,000 | - | 920,000 | 110.30 | 10.25 | 0.1.3 | Eradication of plant growth | 1
3 | Frame |  |  | 815,000 | 815,000 | 97.71 | 9.08 | 2.1.1 | Steel frames | 1
4 | Upper Floors |  |  | 530,000 | 530,000 | 63.54 | 5.90 | 2.2.1 | Floors | 1
5 | Roof |  |  | 415,000 | 415,000 | 49.75 | 4.62 | 2.3.1 | Roof structure | 0.811
6 | Staircases |  |  | 115,000 | 115,000 | 13.79 | 1.28 | 2.4.1 | Stair/ramp structures | 1
7 | External Walls |  |  | 620,000 | 620,000 | 74.33 | 6.91 | 2.7.1 | Walls and partitions | 0.863
8 | Windows and External Doors |  |  | 235,000 | 235,000 | 28.17 | 2.62 | 2.6.2 | External doors | 1
9 | Internal Walls |  |  | 475,000 | 475,000 | 56.95 | 5.29 | 2.7.1 | Walls and partitions | 1
10 | Internal Doors |  |  | 70,000 | 70,000 | 8.39 | 0.78 | 2.8.1 | Internal doors | 1
11 | Floor Finishes |  |  | 93,000 | 93,000 | 11.15 | 1.04 | 3.2.1 | Finishes to floors | 1
12 | Wall Finishes |  |  | 100,000 | 100,000 | 11.99 | 1.11 | 3.1.1 | Wall finishes | 1
13 | Ceiling Finishes |  |  | 642,000 | 642,000 | 76.97 | 7.15 | 3.3.1 | Finishes to ceilings | 1
14 | Fittings |  |  | 32,000 | 32,000 | 3.84 | 0.36 | 4.1.1 | General fittings, furnishings and equipment | 0.607
15 | Sanitaryware |  |  | 15,000 | 15,000 | 1.80 | 0.17 | 5.1.1 | Sanitary appliances | 1
16 | Disposal Installation |  |  | 52,000 | 52,000 | 6.23 | 0.58 | 5.3.3 | Refuse disposal | 0.727
17 | Mechanical Services |  |  | 1,394,422 | 1,394,422 | 167.18 | 15.53 | 5.6.1 | Central heating | 1
18 | Electrical Services |  |  | 1,235,000 | 1,235,000 | 148.06 | 13.76 | 5.8.1 | Electrical mains and sub-mains distribution | 1
19 | Lift Installation |  |  | 170,000 | 170,000 | 20.38 | 1.89 | 5.10.1 | Lifts and enclosed hoists | 1
20 | Builders Work In Connection (BWIC) |  |  | 138,000 | 138,000 | 16.54 | 1.54 | 5.14.1 | Builder’s work in connection with services | 0.848
21 | Site Works |  |  | 520,000 | 520,000 | 62.34 | 5.79 | 0.1.3 | Eradication of plant growth | 0.406
22 | Drainage |  |  | 50,000 | 50,000 | 5.99 | 0.56 | 5.3.1 | Foul drainage above ground | 1
23 24 Measured Work | External Services |  | 88,000 £ 1,033,000 | - 7,806,423 | 88,000 8,839,423 | 10.55 1,059.76 | 0.98 98.45 | 8.7.1 | Water mains supply | 1
25 | Preliminaries Excluding Design Fees | 7.5% | 78,000 | 586,000 | 664,000 | 79.61 | 7.40
26 27 | Design Development Contingency | 1.5% | 20,000 | - 130,000 | 0 150,000 | 17.98 | 1.67 | 5.14.1 | Builder’s work in connection with services | 0.373
28 | Main Contractors Profit, Ovhds, Insurances | 5.0% | 60,000 | 430,000 | 490,000 | 58.75 | 5.46 | 5.14.1 | Builder’s work in connection with services | 0.415
29 | Client Contingency | 5.0% | 60,000 | 448,000 | 508,000 | 60.90 | 5.66
30 | Section A54: Provisional Sums |  |  | 50,000 | 50,000 | 5.99 | 0.56
31 | Estimated Current Building Cost |  | £ 1,251,000 | 9,450,423 | 10,701,423 | 1,282.99 | 119.19 | 6.1.1 | Complete buildings | 0.353
[Extracted via Docling AI (TableFormer) ¦ NRM matching via sentence-transformers]